## Budget Dashboard Template
Budget Dashboard Template
Job Number: J12345
Customer Name: ABC Corp.
Job Description: Custom Furniture Design
Start Date: January 1, 2025
Completion Date: January 15, 2025
Actual Direct Material Costs
Item Description | Measurement Unit |  | Quantity | Unit Cost | Total Cost
Concrete (cubic yards) | Cubic yard |  | 200 | 500 | 100000
Steel Beams | Unit |  | 50 | 500 | 25000
Drywall (sheets) | Sheets |  | 1000 | 10 | 10000
Roofing Materials | n/a |  | 30 | 10 | 300
Flooring (sq. ft.) | Square feet |  | 5000 | 50 | 250000
|  |  |  | Total Direct Material Costs | 385300
Actual Direct Labor Costs
Name | Worker Role |  | Hours worked | Hourly Rate | Total Cost
Camillo | Project Manager |  | 160 | 75 | 12000
John | Site Supervisor |  | 200 | 50 | 10000
Bryan | Electricians |  | 400 | 40 | 16000
Lia | Plumbers |  | 350 | 35 | 12250
Karen | General Labor |  | 800 | 25 | 20000
0
|  |  |  | Total Direct Labor Costs | 70250
Actual Direct Equipment Costs
Equipment Description | Quantity |  | Purchase/Lease cost | Maintenance cost | Total Cost
Excavator | 1 |  | 50000 | 5000 | 55000
Concrete Mixer | 2 |  | 25000 | 7000 | 32000
Cranes | 1 |  | 100000 | 10000 | 110000
Scaffolding | 15 |  | 15000 | 1500 | 16500
0
|  |  |  | Total Direct Equipment Costs | 213500
Actual Overhead Allocation
Overhead Type | Allocation Base | Value | Rate | Allocated Overhead
Office Expenses | Direct Labor | 80000 | 10% | 8000
Insurance | Project Value | 150000 | 5% | 7500
Utilities | Total Materials | 15000 | 2% | 300
Permits/Fees | Flat Rate | 7500 | 1 | 7500
|  |  | Total Overhead Cost | 23300
Planned vs. Actual Costs
Cost Category | Planned Costs |  | Cost Category | Actual Costs | Balance
Direct Material Costs | 300000 |  | Direct Material Costs | 385300 | -85300
Direct Labor Costs | 75000 |  | Direct Labor Costs | 70250 | 4750
Direct Equipment Costs | 209000 |  | Direct Equipment Costs | 213500 | -4500
Overhead Costs | 43470 |  | Overhead Costs | 23300 | 20170
Total Planned Costs | 627470 |  | Total Actual Costs | 692350 | -64880
Free Related Templates
Cost Benefit Analysis Template
Project Budget Template for Excel
Timesheet Template